## Sheet1
IDENTIFIED LEYDEN TOWN FACILITIES MAINTENANCE AND CAPITAL IMPROVEMENT PROJECTS
FACILITY | PRIORITY RANKING |  |  | FISCAL YEAR |  |  |  | POTENTIAL FUNDING SOURCES
|  | 26 | 27 | 28 | 29 | 30 | BUDGET ESTIMATE | MAINTENANCE BUDGET | CIP | FREE CASH and/or STABILIZATION | GRANTS (1) | LOAN-BOND
TOWN OFFICES
Building Shell-
ADA ramp and automatic door (entire project) |  |  | x |  |  |  | 50000 |  |  |  | x
Windows replacement (or elimination) |  |  | x | x |  |  | 75000 |  | x |  | Green Communities
Partial siding replacement |  |  | x | x |  |  | 12-15,000 |  | x |  | x
T111 repair |  |  | x |  |  |  | 3000
Outside insulation and siding over it (entire building post T111 repair) |  |  |  | x |  |  | 250000 |  |  |  | Green Communities
Building Infrastructure- |  |  | x | x |  |  |  | x | x
Building infrastructure upgrades (elec.; HVAC; plumbing, IT, security | [6 empty] | 10000
Window weather sealing & insulation | [10 empty] | Michele waiting for call backs
Identify, trace, electrical panel & circuits |  |  |  | x |  |  | 15000
Unit Ventilators (Community Room/ Assessors) |  |  | x | x | x |  | 35000 |  |  |  | MIIA Grant ($10K)
Furnace replacement |  |  |  |  | x |  | 30000
FIRE DEPT. | [6 empty] | 300000
Building Shell-
Raise roof to allow vechicles to enter/exit
Install roof support; check structural integrity
Repair-replace fasica-soffit trim | [6 empty] | 5000 | x
Electrical - add'l outlets (quads) |  |  | x | x |  |  | 10000 | x
Outside insulation and ALL siding over it | [6 empty] | 25000 |  |  |  | Green Communities + town funds
Window replacement (or covered with insulation) | [6 empty] | 8500 |  | x |  | Green Communities
Furnace replacement |  |  |  | x |  |  | 10000
Operations
Install apparatus ventilation system | [6 empty] | 25000 |  | x |  | x
Building Infrastructure- | [6 empty] | 5-12,000 | x | x | x | x
Replace HVAC system for heating-cooling upgrades for plumbing, electrical
HIGHWAY DEPARTMENT | [9 empty] | x | Green Communities
Building Shell-
Upgrade insulation | [6 empty] | 5-7,500
Replace windows | [6 empty] | 8500 |  | x |  | Green Communities
Make repairs to salt shed (2) |  |  | x |  |  |  | 7500 |  |  |  | Chapter 90
Replace rotten wood under salt shed |  |  | x |  |  |  | 1000 | x |  |  | Chapter 90
Operations- | [6 empty] | 150000 | x |  | x
Feasibility assessment for new building including covered area for storage, improved movement on site | [8 empty] | x
New facility construction | [6 empty] | TBD |  |  |  | x | x
Building Infrastructure- | [7 empty] | x
Upgrades to HVAC, security, plumbing;
electrical | [6 empty] | 15000 |  | x
Ventilation and exhaust increase | [6 empty] | 19000
Furnace replacement |  |  | x |  |  |  | 15000
Electrical upgrades (outlets, tracing) | [6 empty] | 10000
TOWN HALL | [7 empty] | x |  | x
Building Shell-
Upgrade insulation | [6 empty] | 10000 |  | x
Window replacement; siding work | [6 empty] | 70000 |  | x |  | x
Fire exit, assess code requirements
Operations - TBD
Building Infrastructure- | [7 empty] | x
Upgrades to HVAC; plumbing; electrical | [6 empty] | 10 - 15,000
Furnace replacement | [5 empty] | x | 30000
window weathersealing & insulation | [6 empty] | 14500
Identify, trace, electrical panel & circuits | [6 empty] | 15000
OLD PD BUILDING
Building Shell-
Insulation | [6 empty] | 5-6,500 | x | x |  | x
Window replacement | [6 empty] | 7000 |  | x |  | x
Sideing repair | [6 empty] | 15000
Building Infrastructure-
Upgrades to HVAC; plumbing; electrical | [6 empty] | 5-10,000 | x | x |  | x
Operations-
(Based on the condition of the building - assess the long-term use in rerlation to potential expansion of the DPW and upgrading of EMS-Fire Operations | [6 empty] | TBD
Identify, trace, electrical panel & circuits | [6 empty] | 7000
LIBRARY
Building Shell:
A) repair rotting wood | [6 empty] | 5000
B) repair water damage | [6 empty] | 3000
Building Infrastructure: | [6 empty] | 20000
Upgrades to HVAC; plumbing; electrical
(1)- Includes Green Communities funding
(2)- Assume no structural issues with salt shed; work could entail replacing truss gussett plates